## Summary
PMEx Feature QA Tracker
Current phase | Post-fix retest complete; all user stories passed
Generated | 2026-06-25
Canonical workbook | C:\Users\jaswi\OneDrive\Documents\CODE\PMEx-main\outputs\019f0002-09fd-7710-a9a1-84bbd1ae3770\pmex-feature-user-story-tracker.xlsx
Feature/user-story rows | 53
Passed | 53
Failed | 0
Ready for Test | 0
Open documented errors | 0
Workflow | Description | Status | Evidence | Next action
1. Inventory | Audit source, manifest, README, tests, scripts, and UI references. | Complete | 53 user stories created from code and tests. | Done.
2. Test | Run automated, layout, browser, and live/user behavior tests. | Complete | Initial test loop found 3 documented failures. | Done.
3. Fix | Fix logistical and UX errors found during testing. | Complete | ERR-001, ERR-002, and ERR-003 fixed in source/tooling. | Done.
4. Retest | Retest every user story after fixes. | Complete | npm run test:release and npm run test:visual passed after fixes. | Done.
5. Close | Mark the goal complete only when all rows pass or known blockers are documented. | Complete | Workbook shows 53 passed rows and 0 open errors. | Ready to close.

## User Stories
Canonical User Stories
Story ID | Area | Actor | User Story | Trigger / Entry Point | Expected Behavior Based On Code | Source Evidence | Test Method | Priority | Status | Initial Test Result | Errors | Fix Notes | Retest Result
US-001 | Activation and Permissions | Reader | As a reader, I can run the extension only after I explicitly open the toolbar popup or command. | Click extension action or press the registered command | The extension uses MV3 activeTab and scripting permissions, has narrow market host permissions, and cannot read the active page before user activation. | manifest.json:1; scripts/browser-smoke.js:119; test/staticPolicy.test.js:23 | Static policy test; browser smoke pre-activation probe | P0 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-002 | Activation and Permissions | Reader | As a returning user, I am routed from a stale detached popup launcher back to the canonical toolbar popup. | Open legacy expanded URL with sourceTabId while manifest default popup is missing | The popup shows an updating state, schedules chrome.runtime.reload, and does not begin article extraction. | src/popup/popup.js:92; src/popup/popup.js:105; test/popupController.test.js:424 | Controller unit test | P1 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-003 | Activation and Permissions | Reader | As a reader, refreshing from the popup still targets the original article tab rather than the popup surface. | Refresh after the active browser tab is chrome-extension:// popup | The controller caches the source tab id or uses sourceTabId, ignores internal browser URLs, and reuses the original article snapshot when needed. | src/popup/popup.js:38; src/popup/popup.js:412; src/popup/popup.js:434; test/popupController.test.js:510 | Controller unit test; browser smoke | P0 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-004 | Article Extraction | Reader | As a reader, the extension extracts readable article text and metadata from the active page. | Popup starts on a readable article page | Readability, the extractor, and the runner are injected into the active tab; the result contains readable text, title, metadata, and headings. | src/popup/popup.js:439; src/lib/articleExtractor.js:254; src/content/runExtraction.js:14; test/articleExtractor.test.js:16 | Extractor unit tests; browser smoke | P0 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-005 | Article Extraction | Reader | As a reader, article extraction uses semantic page regions when publisher markup contains sidebar noise. | Readable article page with noisy sidebars or common blog containers | The semantic fallback scores article-like containers and returns the main article body instead of large unrelated sidebars. | src/lib/articleExtractor.js:128; src/lib/articleExtractor.js:146; src/lib/articleExtractor.js:162; test/articleExtractor.test.js:40 | Extractor unit tests; saved fixture tests | P1 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-006 | Article Extraction | Reader | As a reader, I can select article text and have the extension prefer that selected text when it is the clearest source. | Run extension with a long text selection on a sparse page | Selected text above the threshold is preferred over weaker body extraction and still returns a readable article object. | src/lib/articleExtractor.js:185; src/lib/articleExtractor.js:226; test/articleExtractor.test.js:81; test/articleFixtures.test.js:53 | Extractor unit tests; fixture tests | P1 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-007 | Article Extraction | Reader | As a reader, I get a clear no-readable-article state instead of a broken popup on unsupported pages. | Open popup on a page with too little article body text | The popup stops before market search, reports No readable article, and renders an explanatory empty state. | src/lib/articleExtractor.js:271; src/popup/popup.js:1382; test/popupController.test.js:1334 | Extractor tests; controller unit test | P0 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-008 | Privacy and Local Analysis | Reader | As a privacy-conscious reader, my full article text is analyzed locally and not sent to an AI service. | Run extension on an article | The extension loads local scripts and a JSON classifier model; static policy checks find no page monitoring or AI-service calls. | README.md:7; src/popup/popup.js:270; src/lib/articleSignals.js:1052; test/staticPolicy.test.js:44 | Static policy test; source inspection | P0 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-009 | Local Article Model | Reader | As a reader, the extension classifies article topic, market angles, and query hints from the local JSON model. | Article text is extracted | The local classifier returns topic, confidence, market angles, excluded angles, subtopics, relevant entity types, and query hints. | src/lib/articleSignals.js:595; src/lib/articleSignals.js:702; test/articleClassifier.test.js:14 | Classifier unit tests | P0 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-010 | Local Article Model | Reader | As a reader, generated search queries are compact and centered on the article's central entities and angle. | Analyze an article with entities, keywords, and classifier hints | Queries include high-signal entities and angle hints while suppressing incidental people, places, crypto assets, sports leakage, and product false positives. | src/lib/articleSignals.js:825; src/lib/articleSignals.js:910; test/articleSignals.test.js:157; test/articleSignals.test.js:172 | Article signal unit tests | P0 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-011 | Local Article Model | Reader | As a reader, the local model remains deterministic and fast enough for a popup. | Analyze representative article fixtures | Keyword scoring is deterministic and the local model stays within the defined latency budget. | src/lib/articleSignals.js:219; test/articleSignals.test.js:60; test/articleClassifier.test.js:107 | Unit tests with latency budget | P1 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-012 | Polymarket Search | Reader | As a reader, related Polymarket events are fetched from public-search, similar events, and tag-expanded inventory. | Analyze article and search for related events | The app builds tuned public-search requests from generated queries, optionally fetches similar title events and central entity tag inventory, then normalizes candidates. | src/lib/polymarket.js:1477; src/lib/polymarket.js:1503; src/lib/polymarket.js:1884; test/polymarket.test.js:835 | Polymarket unit tests; live smoke | P0 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-013 | Polymarket Search | Reader | As a reader, Polymarket API payloads normalize safely across event, market, outcome, image, and movement variants. | Receive Gamma public-search or event API payloads | Stringified arrays, binary and non-binary outcomes, image variants, condition IDs, volume, movement, dates, and optional missing fields are normalized without throwing. | src/lib/polymarket.js:193; src/lib/polymarket.js:250; src/lib/polymarket.js:407; src/lib/polymarket.js:487; test/polymarket.test.js:18 | Polymarket unit and fixture tests | P0 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-014 | Polymarket Search | Reader | As a reader, inactive, closed, expired, pending, or unavailable markets are hidden. | Search returns stale or non-live candidates | The app rejects closed, resolved, archived, cancelled, pending-review, unavailable, and past-end-date markets while keeping approved active markets. | src/lib/polymarket.js:299; src/lib/polymarket.js:334; src/lib/polymarket.js:377; test/polymarket.test.js:375 | Polymarket unit tests; controller filter test | P0 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-015 | Polymarket Ranking | Reader | As a reader, market matches are ranked by relevance instead of only popularity. | Candidate markets are available for an article | Ranking combines entity, keyword, title overlap, topic, classifier angle, quality, trend boosts, and penalties; irrelevant trends do not override weak relevance. | src/lib/polymarket.js:1175; src/lib/polymarket.js:1248; test/polymarket.test.js:334; test/polymarket.test.js:660 | Ranking unit tests; golden fixture tests | P0 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-016 | Polymarket Ranking | Reader | As a reader, plausible lower-confidence markets can fill sparse related results without promoting rejected markets. | Strong related results are sparse | The related search reruns at maybe confidence, includes maybe matches, and merges them without duplicates only when useful. | src/popup/popup.js:1277; src/popup/popup.js:1301; test/popupController.test.js:1164; test/polymarket.test.js:1078 | Controller and ranking unit tests | P1 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-017 | Polymarket Ranking | Reader | As a reader, child markets collapse into parent event cards with enough child options retained for detail views. | Multiple markets belong to the same Polymarket event | The parent event is ranked with article context, uses the best child for trade view details, preserves option labels, and keeps up to the configured child-market limit. | src/lib/polymarket.js:1408; src/lib/polymarket.js:1433; test/polymarket.test.js:199; test/polymarket.test.js:228 | Polymarket grouping tests; render tests | P0 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-018 | Market Metadata | Reader | As a reader, public position holder counts can enrich Polymarket groups without blocking rendering. | Polymarket groups have condition IDs | The app requests market position summaries with timeout protection, caches duplicate condition IDs, and leaves groups unchanged on failures. | src/lib/polymarket.js:1686; src/lib/polymarket.js:1838; src/popup/popup.js:388; test/polymarket.test.js:290 | Polymarket unit tests; controller unit test | P2 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-019 | Polymarket Search | Reader | As a reader, partial Polymarket API failures do not break the full search if at least one request succeeds. | One generated query/API request fails while others succeed | The app uses fulfilled responses and only throws when every request fails. | src/lib/polymarket.js:1905; test/polymarket.test.js:799 | Polymarket unit tests | P1 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-020 | Hyperliquid | Trader | As a trader, Hyperliquid assets can appear alongside prediction markets when relevant to the article or query. | Article or manual query mentions a supported asset alias | The app fetches Hyperliquid meta/context data, matches aliases, ranks by article/query relevance, and normalizes venue candidates. | src/lib/hyperliquid.js:200; src/lib/hyperliquid.js:237; src/lib/hyperliquid.js:254; test/hyperliquid.test.js:75 | Hyperliquid unit tests; browser smoke | P1 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-021 | Hyperliquid | Trader | As a trader, Hyperliquid trending markets are available in the Trending tab. | Open Trending tab | The venue returns top assets by 24h notional volume and groups them without changing their Hyperliquid source identity. | src/lib/hyperliquid.js:275; src/lib/hyperliquid.js:289; test/hyperliquid.test.js:107 | Hyperliquid unit tests; controller unit test | P2 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-022 | Popup Shell | Reader | As a reader, the popup clearly shows its loading and phase progression while it scans. | Popup starts related-market scan | Controls are disabled, loading is visible, and phase history includes reading, extracting, searching, and complete or error. | src/popup/popup.js:68; src/popup/popup.js:80; src/popup/popup.js:1334; test/popupController.test.js:368 | Controller unit tests; browser smoke | P0 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-023 | Popup Shell | Reader | As a reader, API or extension failures render an error state instead of leaving stale loading UI. | Market search throws | The popup marks status as error, enables controls again, and shows a market-first error state with the failure message. | src/popup/popup.js:1390; src/popup/render.js:1645; test/popupController.test.js:1350; test/popupRender.test.js:727 | Controller and renderer unit tests | P0 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-024 | Manual Search | Reader | As a reader, I can search markets manually without rereading the article. | Submit the market search form with at least two characters | The app searches Polymarket and Hyperliquid, shows Search results, preserves the article extraction call count, and asks for at least two characters for short input. | src/popup/popup.js:1406; src/popup/popup.js:1536; test/popupController.test.js:1367; test/polymarket.test.js:987 | Controller unit test; browser interaction smoke | P0 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-025 | Tabs | Reader | As a reader, the Trending tab loads active markets without rerunning article extraction. | Click Trending tab | The tab becomes active, stale pagination/trade view state is cleared, trending sources are queried, and results or empty state render under Trending markets. | src/popup/popup.js:1464; src/popup/popup.js:1561; test/popupController.test.js:1414 | Controller unit test; browser interaction smoke | P1 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-026 | Tabs | Reader | As a reader, the Watchlist tab is present but honestly empty until saved markets exist. | Click Watchlist tab | The app clears stale related/search results, sets Watchlist active, and renders No watchlist markets yet / Saved markets will appear here. | src/popup/popup.js:695; src/popup/popup.js:1562; test/popupController.test.js:1393 | Controller unit test; browser interaction smoke | P2 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-027 | Tabs | Reader | As a reader, returning to Relevant Markets reuses the latest related results or empty state before rerunning extraction. | Click Relevant Markets after another tab | Cached related groups render when available; otherwise cached no-match state renders, or a new run starts if no article has been analyzed. | src/popup/popup.js:1540; src/popup/popup.js:1545; src/popup/popup.js:1554 | Source review; covered indirectly by controller tests | P2 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-028 | Menu and Feedback | Reader | As a reader, the Connect/Refresh action reruns matching and reports the real outcome. | Click Connect in the menu | The menu closes, matching reruns, a sighted surface message reports Connected, No readable article, or Not connected based on the final phase. | src/popup/popup.js:709; src/popup/popup.js:1515; test/popupController.test.js:1437; test/popupController.test.js:1546 | Controller unit tests; browser interaction smoke | P0 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-029 | Results List | Reader | As a reader, result cards are compact, collapsed by default, and scannable. | Related, search, or trending results render | Each parent card shows image or fallback, title, source badge, main quote/value, movement, and a safe market URL without child-market cards or score badges. | src/popup/render.js:1482; src/popup/render.js:1520; test/popupRender.test.js:66; test/popupRender.test.js:333 | Renderer unit tests; layout smoke; browser smoke | P0 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-030 | Results List | Reader | As a reader, missing or broken market images do not leave blank cards. | A market image URL is missing, invalid, or fails to load | The renderer uses category-aware fallback glyphs and replaces broken images once the error event fires. | src/popup/render.js:235; src/popup/render.js:267; test/popupRender.test.js:295 | Renderer unit tests; layout smoke | P2 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-031 | Results List | Reader | As a reader, I can sort rendered markets by best match, volume, or ending soon. | Click the sort control | The sort mode cycles Best match -> Volume -> Ending soon and the current groups rerender in the selected order. | src/popup/popup.js:44; src/popup/popup.js:503; src/popup/popup.js:1637 | Browser smoke interaction; source review | P2 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-032 | Results List | Reader | As a reader, long related result sets progressively reveal more cards instead of being capped at four. | Related search returns more than the initial batch | The list renders eight groups first, then Show more or the scroll sentinel reveals the next batch while preserving sorted state. | src/popup/popup.js:10; src/popup/popup.js:529; src/popup/popup.js:540; test/popupController.test.js:1270 | Controller unit tests; browser smoke | P1 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-033 | Results List | Reader | As a reader, the header collapses smoothly while I scroll results and restores at top. | Scroll results region down and back up | Topbar and tabs animate height, opacity, and translate values; the shell gains/removes is-results-scrolled and pagination preserves scroll state. | src/popup/popup.js:175; src/popup/popup.js:194; test/popupController.test.js:441; test/popupController.test.js:1300 | Controller unit tests; layout smoke | P2 | Retest Passed | Failed: browser interaction smoke timed out before confirming menu behavior in a completed result flow. | ERR-001 | ERR-001: menu wrapper remains clickable while collapsed non-menu topbar content is inert. | Passed post-fix: npm run test:release and npm run test:visual.
US-034 | Card Expansion | Reader | As a reader, I can expand and collapse a market card with mouse or keyboard. | Click card/chevron or press Enter/Space on a card/chevron | The selected card toggles expanded state, other cards collapse as appropriate, and measured height animation avoids layout jumps. | src/popup/popup.js:834; src/popup/popup.js:874; src/popup/popup.js:1686; test/popupController.test.js:536 | Controller unit tests; browser interaction smoke | P0 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-035 | Card Expansion | Reader | As a reader, expanded event cards show useful child options without overwhelming the popup. | Expand a grouped parent event with many child markets | The renderer shows up to six scenario rows, adds Show more for hidden rows, and Show more reveals all grouped options without opening trade view. | src/popup/render.js:12; src/popup/render.js:1394; src/popup/popup.js:897; test/popupController.test.js:629 | Renderer and controller unit tests; layout smoke | P1 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-036 | Trade View | Trader | As a trader, clicking an expanded date/market row opens an internal trade preview instead of navigating away. | Click a market scenario row inside an expanded card | The app finds the candidate, renders the trade view, resets scroll, and does not open a new browser tab. | src/popup/popup.js:795; src/popup/popup.js:938; src/popup/popup.js:1659; test/popupController.test.js:536 | Controller unit tests; browser smoke | P0 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-037 | Trade View | Trader | As a trader, the trade preview shows a complete market surface with nav, hero, chart, ticket, and order book. | Open internal trade view | The view renders back and more buttons, market title, source badge, image, volume/end-date meta, chart, order ticket, and bid/ask order book. | src/popup/render.js:1658; src/popup/render.js:1737; test/popupRender.test.js:385; scripts/browser-smoke.js:498 | Renderer unit tests; layout smoke; browser smoke | P0 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-038 | Trade View | Trader | As a trader, Polymarket CLOB data hydrates the trade chart and order book when available. | Open a Polymarket market with CLOB token IDs | The app fetches book and price history with timeouts, normalizes bid/ask rows and history, then preserves active range/side/amount/action state when hydration completes. | src/lib/polymarket.js:1784; src/popup/popup.js:957; test/popupController.test.js:883; test/popupController.test.js:960 | Unit tests; browser smoke optional TradingView check | P0 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-039 | Trade View | Trader | As a trader, chart range controls update the visible chart state. | Click 1D, 1W, 1M, 1Y, or ALL in trade view | The active range button changes, SVG fallback path/marker/date/price update, and TradingView visible range is updated when mounted. | src/popup/render.js:1040; src/popup/render.js:1072; src/popup/popup.js:1183; test/popupController.test.js:812 | Renderer/controller unit tests; browser smoke | P1 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-040 | Trade View | Trader | As a trader, order-ticket controls update side, amount, estimates, and preview feedback. | Change side, type amount, click MAX, or click Buy | Buy label and estimate update for selected side/unit, MAX sets $1,000, and Buy shows a read-only trade preview message. | src/popup/render.js:1184; src/popup/popup.js:1035; src/popup/popup.js:1170; src/popup/popup.js:1628; test/popupController.test.js:771 | Controller unit tests; browser smoke | P0 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-041 | Trade View | Trader | As a trader, the trade order book updates when I switch sides and uses live rows when available. | Switch selected side in trade view | Bid/ask rows redraw from provided book data or deterministic fallback rows, with depth bars and formatted price/share/total cells. | src/popup/render.js:1149; src/popup/render.js:1281; src/popup/popup.js:1146; test/popupRender.test.js:433 | Renderer/controller unit tests; browser smoke | P1 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-042 | Trade View | Trader | As a trader, the trade action menu exposes Settings, Connect, and Information actions. | Click more button in trade view | The popover opens/closes, updates aria-expanded, actions show visible status messages, and outside/Escape can dismiss it. | src/popup/render.js:1691; src/popup/popup.js:1229; src/popup/popup.js:1572; test/popupController.test.js:700 | Controller unit tests; browser smoke | P1 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-043 | Trade View | Trader | As a trader, Back returns me to the market list without losing the result set. | Click Back in trade view | TradingView widgets unmount, trade view class is removed, the previous related/search/trending list restores, and no external link opens. | src/popup/popup.js:224; src/popup/popup.js:913; src/popup/popup.js:1564; scripts/browser-smoke.js:556 | Controller unit tests; browser smoke | P0 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-044 | Trade View | Trader | As a trader, Hyperliquid trade previews use asset-market semantics instead of fake binary odds. | Open a Hyperliquid result in trade view | The ticket uses Long/Short, asset mark price, contracts estimate, Hyperliquid source color, and does not invent Yes/No or 1c fallbacks. | src/popup/render.js:756; src/popup/render.js:1184; test/popupRender.test.js:524; test/popupController.test.js:1052 | Renderer/controller unit tests; layout smoke; browser smoke | P0 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-045 | TradingView | Trader | As a trader, the packaged TradingView chart can mount inside the extension under MV3 CSP. | Open trade view with TradingView available | The adapter loads packaged assets, rewrites inline iframe script/style to extension-safe files, creates datafeed bars, and updates range through the widget. | src/popup/tradingview.js:200; src/popup/tradingview.js:268; src/popup/tradingview.js:415; test/tradingView.test.js:65 | TradingView unit tests; optional browser smoke with --verify-tradingview | P1 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-046 | Menu and Accessibility | Keyboard user | As a keyboard user, the profile/action menu is reachable and dismissible. | Click or arrow into the menu button, use Arrow/Home/End/Escape, or click outside | The popup toggles is-menu-open, aria-expanded, aria-hidden, moves focus through menu items, wraps focus, closes on outside click or Escape, and returns focus to the trigger when appropriate. | src/popup/popup.js:727; src/popup/popup.js:747; src/popup/popup.js:1752; test/popupController.test.js:1485 | Controller unit tests; browser smoke | P0 | Retest Passed | Failed: browser interaction smoke timed out waiting for menu opened/profile focus. | ERR-001 | ERR-001: menu wrapper remains clickable while collapsed non-menu topbar content is inert. | Passed post-fix: npm run test:release and npm run test:visual.
US-047 | Menu and Feedback | Reader | As a reader, profile, settings, and privacy actions provide visible feedback. | Open menu and click Profile, Settings, or Information | The menu closes and a surface message plus status update explains Default profile, read-only matching, or local/no-data-leaves-device privacy behavior. | src/popup/popup.js:1731; src/popup/popup.js:1738; src/popup/popup.js:1745; test/popupController.test.js:1437 | Controller unit tests; browser smoke | P1 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-048 | Menu and Accessibility | Assistive technology user | As an assistive technology user, live status updates are available without adding hidden keyboard traps. | Popup changes status or renders hidden utility controls | Status and surface regions use aria-live, menu roles are present, and static policy checks find no tabbable hidden utilities. | src/popup/popup.html:118; src/popup/popup.html:119; test/staticPolicy.test.js:57 | Static policy tests; source review | P1 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-049 | Responsive Layout | Reader | As a reader, the popup is usable at the anchored extension sizes and narrow responsive widths. | Render popup at 500x850, 500x510, 390px, and 320px viewports | There is no horizontal overflow, cards remain visible, first meaningful content is in view, the shell fits, and trade view remains scrollable. | src/popup/popup.css:28; src/popup/popup.css:2169; scripts/popup-layout-smoke.js:19; test/staticPolicy.test.js:99 | Layout smoke script; browser smoke screenshot | P0 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-050 | Real Browser Flow | Reader | As a reader, the real unpacked extension opens an anchored popup through a user-style browser event. | Run browser smoke against a live article URL | Chrome registers the action command, pre-activation read is blocked, the popup opens full-height, reaches final state, and renders valid supported venue links or a valid no-match state. | scripts/browser-smoke.js:93; scripts/browser-smoke.js:598; docs/release-verification.md:17 | Browser smoke script | P0 | Retest Passed | Failed: browser smoke direct-open check timed out on third-party Polymarket DOMContentLoaded. | ERR-002 | ERR-002: direct-open venue navigation is best-effort while supported hosts are still asserted. | Passed post-fix: npm run test:release and npm run test:visual.
US-051 | Real Browser Flow | Reader | As a reader, browser smoke can exercise end-to-end popup interactions. | Run browser smoke with verify interactions and verify expanded | The smoke checks Trending, manual Search, sort, footer/menu information, refresh, trade view, range, side, max, action popover, buy preview, back, and supported venue navigation. | scripts/browser-smoke.js:390; scripts/browser-smoke.js:498; package.json:11 | Browser smoke interaction script | P0 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-052 | Live QA | Maintainer | As a maintainer, I can run live article and Polymarket schema checks before release. | Run npm live or release verification scripts | Live Polymarket schemas parse, current article feeds extract and match as expected, and known caveats are documented for human relevance review. | package.json:8; package.json:9; docs/release-verification.md:11; scripts/live-article-qa.js:1 | Live QA scripts; release script | P1 | Retest Passed | Passed in initial automated, layout, live, or browser coverage before story-specific fixes. |  |  | Passed post-fix: npm run test:release and npm run test:visual.
US-053 | Developer Tooling | Maintainer | As a maintainer, command-line argument parsing and QA utilities support repeatable test scripts. | Run test scripts with flags such as --url, --verify-interactions, or --visual-reference | Arg parsing returns first/last values, positive numeric flags validate consistently, and QA utilities discover articles and write timestamped artifacts. | scripts/cliArgs.js:1; scripts/qaUtils.js:114; test/cliArgs.test.js:8 | CLI utility unit tests; script smoke | P2 | Retest Passed | Failed: browser smoke direct-open check was too brittle; visual npm script also exited with usage. | ERR-002; ERR-003 | ERR-002/ERR-003: browser smoke records third-party navigation errors; visual script now supplies latest/latest defaults. | Passed post-fix: npm run test:release and npm run test:visual.

## Errors
Documented Errors
Issue ID | Story IDs | Severity | Type | Reproduction Steps | Observed Behavior | Expected Behavior | Evidence | Likely Source | Status | Fix | Retest
ERR-001 | US-033; US-046 | P1 | UX | Run node scripts/browser-smoke.js --verify-interactions --verify-expanded --skip-clicks after result interactions. | The real-extension smoke timed out waiting for the profile menu to open and focus the Profile action after a completed result flow. | The visible profile/menu control remains clickable and opens the action menu with aria-expanded=true and Profile focused. | Timeout at menu opened; CSS had .is-results-scrolled .rainbow-topbar pointer-events: none. | src/popup/popup.css | Fixed | Kept collapsed non-menu topbar content inert while preserving pointer events for .menu-wrap. | Passed: node scripts/browser-smoke.js --verify-interactions --verify-expanded --skip-clicks; npm run test:browser; npm run test:release.
ERR-002 | US-050; US-053 | P2 | QA tooling | Run npm run test:browser with default external direct-open checks. | The smoke failed after reaching the trade view because a Polymarket venue page did not finish DOMContentLoaded within 45 seconds. | The browser smoke should fail on malformed app-generated venue URLs, not third-party page-load slowness after the supported host is known. | page.goto timeout at scripts/browser-smoke.js direct-open loop for a polymarket.com event URL. | scripts/browser-smoke.js | Fixed | Made direct-open navigation best-effort, records navigationError, and still rejects unsupported final hosts. | Passed: npm run test:browser; npm run test:release.
ERR-003 | US-053 | P2 | QA tooling | Run npm run test:visual. | The npm script exited with usage because compare-popup-reference.js requires --reference and --actual arguments. | The package visual smoke command is runnable and still allows explicit baseline comparison when supplied. | Usage: node scripts/compare-popup-reference.js --reference=reference.png --actual=latest. | package.json | Fixed | Changed test:visual to compare --reference=latest --actual=latest as a default smoke check. | Passed: npm run test:visual after browser smoke; npm run test:release remained green.

## Test Runs
Test Run Log
Run ID | Date | Command | Scope | Result | Evidence / Notes | Story IDs
TR-001 | 2026-06-25 | npm test | Initial automated behavior loop | Passed | 138 node:test unit, renderer, controller, policy, ranking, TradingView, extractor, and CLI tests passed. | US-001:US-049; US-053
TR-002 | 2026-06-25 | npm run test:layout | Initial responsive and visual-layout loop | Passed | Generated popup, compact, mid, narrow, Polymarket trade, and Hyperliquid trade screenshots; script exited 0. | US-029:US-033; US-037; US-041; US-049
TR-003 | 2026-06-25 | npm run test:browser | Initial real-extension browser loop | Failed | Default browser smoke reached popup/trade view but failed while waiting for external Polymarket venue page DOMContentLoaded. | US-050; US-053
TR-004 | 2026-06-25 | node scripts/browser-smoke.js --verify-interactions --verify-expanded --skip-clicks | Initial browser interaction loop without external direct opens | Failed | Popup reached Local scan complete with 7 results, then timed out waiting for menu opened/profile focus. | US-033; US-046
TR-005 | 2026-06-25 | npm run test:visual | Initial visual smoke loop | Failed | Script exited with usage because package.json invoked compare-popup-reference.js without required reference/actual arguments. | US-053
TR-006 | 2026-06-25 | npm run test:browser | Post-fix browser behavior loop | Passed | Both browser-smoke passes completed: activation, popup results, internal trade view, trending, manual search, sort, menu, footer info, refresh, and expanded popup. | US-001; US-003; US-004; US-012:US-021; US-024:US-050; US-053
TR-007 | 2026-06-25 | npm run test:live | Post-fix live API and article loop | Passed | Polymarket live smoke checked 10/10 endpoints and parsed 563 candidates; live article QA processed 8 readable articles across 8 categories. | US-012:US-021; US-052
TR-008 | 2026-06-25 | npm run test:release | Post-fix full release loop | Passed | Release script passed unit tests, layout smoke, live Polymarket/article QA, and browser smoke end to end. | US-001:US-053
TR-009 | 2026-06-25 | npm run test:visual | Post-fix visual smoke loop | Passed | Compared latest browser-smoke screenshot to latest reference smoke path; PNG parser and threshold report exited 0. | US-001:US-053

## Lazyweb References
Lazyweb UI Reference Notes
Query | Reference | Platform | URL | Pattern Note
browser extension popup dashboard cards | music-speed-changer | desktop | https://musicspeedchanger.com/forum/index.php | Browser-extension dashboard pattern with recent update rows, filtering, and status indicators. Relevant to constrained popup state feedback and action clarity.
browser extension popup dashboard cards | demo-gorilla | desktop | https://demogorilla.com/docs/collections | Browser-extension app pattern with left navigation and central empty/sign-in prompt. Relevant to clear placeholders such as Watchlist and no-readable states.
financial trading dashboard result cards | yahoo-finance | desktop | https://finance.yahoo.com/markets/prediction/earnings/ | Prediction-market dashboard pattern with probability, volume, filtering, and Yes/No actions. Relevant to compact market cards and quote hierarchy.
financial trading dashboard result cards | investing-com | desktop | https://www.investing.com/charts | Trading dashboard pattern with primary chart, timeframe selectors, and market widgets. Relevant to trade view chart and range controls.
financial trading dashboard result cards | activ-financial-systems | desktop | https://www.options-it.com/news/ | Financial news/feed cards with a right-side capture/control panel. Relevant to article-to-market research surfaces and clear action grouping.